## Sheet1
|  | September | [28 empty] | October | [30 empty] | November | [29 empty] | December
Phases | Tasks | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Phase 1
Create milestones for the project
Create mock-ups of the application
Perform usability testing
Search for textbook API to use
Phase 2
Create requirements document
Create GUI Skeleton
Phase 3
Create relational database of all information
Add information to database from API
Phase 4
Add backend functionality (search, sell)
Add messages for items already sold
Phase 5
Improve GUI to make it final
Finish backend functionality
Make GUI mobile-friendly & test on devices
Usability testing
Phase 6
Authentication of users using Oswego emails
Create final application logo
Put everything on server so can be accessed
Phase 7
Testing & Debugging
Phase 8
Work on the email interaction once sold
Add ability for seller to set preferred meetup area
Phase 9
Deployment and final degbugging and testing
If time permits, create iOS and Android application